## Sheet1
| Total for each stage |  |  | Transmission between stages
2 or 3 versions - only one can be chosen - decision can be made later on
minimum and maximum number of days for each stage and in total
number of kilometers, in total per stage
The most probably number of days, if no problem occurs
[6 empty] | Time (days) |  |  | Time in total |  |  |  | Distance (km) |  |  | Estimated date
Stage | Name | Description | Where | From | To | Min | opti | Max | Min | opti | Max | km/day | GPS | Map | The most probably | 2013-01-25 | Best time to visit | Comments | Status
to be booked
maps,boxes,food, bike, freight, car
CS to be found
1 | Running | Running |  | Cabo Froward | Punta Arenas | 3 | 3 | 5 |  |  |  | 30 | 97 |  | 110 | 2013-01-28 |  |  | done
|  | Recovery | Punta Arenas |  |  | 0 | 1 | 3 | [7 empty] | 2013-01-29 |  |  | CS to be found
|  | Running |  | Punta Arenas | Puerto Natales | 4 | 7 | 8 |  |  |  | 35 |  | 238 | 238 | 2013-02-05 |  |  | to be improved with better map
[5 empty] | Total Running | 7 | 11 | 16 | 7 | 11 | 16 |  |  |  | 348
| Transmission | Recovery | Puerto Natales |  |  | 1 | 1 | 3 | 8 | 12 | 19 |  |  |  |  | 2013-02-06 |  |  | contact Iza
2 | Walking | Torres del Paine |  | Puerto Natales | Laguna Amarga | 6 | 7 | 8 |  |  |  | 20 | 140 |  | 150 | 2013-02-13 |  | In Torres del Paine
|  |  | version 1 | Laguna Amarga | El Calafate | 3 | 4 | 5 |  |  |  | 30 |  | 105 | 105 |  |  | without Perito Moreno | to be improved with better map
|  |  | version 2 | Laguna Amarga | close Calafate | 7 | 8 | 10 |  |  |  | 30 | 210 | 230 | 230 |  |  | if not obtain the permit | to be improved with better map
[5 empty] | version 1 or 2 | 3 | 8 | 10 | [6 empty] | 230 | 2013-02-21
|  | Recovery | El Calafate |  |  | 0 | 0 | 3 | [7 empty] | 2013-02-21 |  | or other place if version 3 | CS to be found
|  | Pampa |  | El Calafate | Rio Mayer | 11 | 13 | 16 |  |  |  | 30 | 350 |  | 385 | 2013-03-06 |  | shortcut via pampa
|  | Recovery | Rio Mayer |  |  | 1 | 1 | 3 | [7 empty] | 2013-03-07
|  | Andes |  | Rio Mayer | Chochrane | 6 | 7 | 9 |  |  |  | 20 | 139 |  | 155 | 2013-03-14 |  |  | done
|  | Recovery | Chochrane |  |  | 1 | 1 | 3 | [7 empty] | 2013-03-15 |  |  | CS to be found
|  |  |  | Chochrane | Coihaique | 10 | 13 | 16 |  |  |  | 30 | 289 | 320 | 320 | 2013-03-28 |  |  | done
|  | Recovery | Coihaique |  |  | 1 | 1 | 3 | [7 empty] | 2013-03-29 | less rain Sep-Feb |  | CS to be found
|  |  |  | Coihaique | Chaiten | 11 | 14 | 17 |  |  |  | 35 | 401 | 370 | 440 | 2013-04-12 |  | inc. 1-2 days in Queulat NP | done
|  | Recovery | Chaiten |  |  | 1 | 2 | 3 | [7 empty] | 2013-04-14 |  |  | someone to be found
|  |  |  | Chaiten | Cochamo | 16 | 22 | 26 |  |  |  | 15 | 255 | 58 | 280 | 2013-05-06 |  |  | heavy backpack, trackless
[5 empty] | Total Walking | 67 | 89 | 117 | 75 | 101 | 136 |  |  |  | 1960 | 125 km might be less
| Transmission | Recovery | Puerto Montt/Cochamo |  |  | 1 | 2 | 4 | 76 | 103 | 140 |  |  |  |  | 2013-05-08 | Oct-Feb, ok Sep-Mar | side trip to Puerto Montt | bicycle pick up to be found
3 | Cycling | Cycling |  | Cochamo | Mendoza | 14 | 14 | 21 |  |  |  | 75 |  | 1390 | 1390 | 2013-05-22
|  | Recovery | Mendoza |  |  | 1 | 1 | 3 | [7 empty] | 2013-05-23 |  | climbing papers arrange | climbing storage to be found
|  |  |  | Mendoza | Valparaiso | 4 | 4 | 6 |  |  |  | 60 |  | 165 | 385 | 2013-05-27
[5 empty] | Total Cycling | 19 | 19 | 30 | 95 | 122 | 170 |  |  |  | 1775
| Transmission | Recovery | Puente del Inca |  |  | 0 | 0 | 0 | 95 | 122 | 170 |  |  |  |  | 2013-05-27 |  | side trip to Puerto Montt | bicycle pick up
4 | Climbing | Climbing | return trip | Puente del Inca | Aconcagua | 0 | 0 | 0 |  |  |  |  | 50 |  | 0 | 2013-05-27 | Nov-Feb |  | permits issued before 15 March
[5 empty] | Total Climbing | 0 | 0 | 0 | 95 | 122 | 170 |  |  |  | 0
| Transmission | Recovery | Puente del Inca |  |  | 0 | 0 | 0 | 95 | 122 | 170 |  |  |  |  | 2013-05-27
5 | Cycling | Cycling |  | Puente del Inca | Valparaiso | 0 | 0 | 0 |  |  |  | 100 |  | 220 | 0 | 2013-05-27
[5 empty] | Total Cycling | 0 | 0 | 0 | 95 | 122 | 170 |  |  |  | 0
| Transmission | Recovery | Valparaiso |  |  | 5 | 5 | 8 | 100 | 127 | 178 |  |  |  |  | 2013-06-01 | Sep-Apr |  | sailboat searching
4 | Sailing |  |  | Valparasiso | Antofagasta | 8 | 14 | 20 | [6 empty] | 1305 | 2013-06-15
|  |  |  | version 1 | Sailing | 8 | 12 | 14 |  |  |  | 100 |  | 1090 | 1090
|  |  |  | version 2 | Cycling | 13 | 14 | 20 |  |  |  | 75 |  | 1306 | 1305
[5 empty] | Total Sailing/Cycling | 8 | 14 | 20 | 108 | 141 | 198 |  |  |  | 1305 | 215 km might be less
| Transmission | Recovery | Antofagasta |  |  | 2 | 2 | 4 | 110 | 143 | 202 |  |  |  |  | 2013-06-17 | Anytime |  | desert cart pick up to be found
5 | Walking | Atacama |  | Antofagasta | San Pedro de A. | 9 | 12 | 15 |  |  |  | 25 | 287 |  | 315 | 2013-06-29
|  | Recovery | San Pedro de A. |  |  | 1 | 2 | 3 | [7 empty] | 2013-07-01 | Jun-Oct |  | Victor friends
|  | Salar |  | San Pedro de A. | Sabaya | 20 | 25 | 35 |  |  |  | 20 | 550 |  | 605 | 2013-07-26 | Apr-Nov, cold May-Aug
|  | Altiplano | + Sajama climb | Sabaya | Copacabana | 17 | 22 | 28 |  |  |  | 25 | 440 |  | 485 | 2013-08-17 |  |  | Included climbing Sajama
|  |  | climbing | Sajama |  | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0
|  | Altiplano |  | Sabaya | Copacabana | 0 | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 2013-08-17
[5 empty] | Total | 47 | 61 | 81 | 157 | 204 | 283 |  |  |  | 1405
| Transmission | Recovery | Copacabana |  |  | 2 | 3 | 5 | 159 | 207 | 288 |  |  |  |  | 2013-08-20 |  |  | Boat searching,CS to be found
6 | Paddling |  |  | Copacabana | Sicuani | 1 | 1 | 1 |  |  |  | 20 | 13 |  | 15 | 2013-08-21
|  | Titicaca |  | Sicuani | Ispaya | 2 | 2 | 3 |  |  |  |  | 32 |  | 32 | 2013-08-23
[5 empty] | Total | 3 | 3 | 4 | 162 | 210 | 292 |  |  |  | 47
| Transmission | Recovery | Ispaya |  |  | 1 | 2 | 2 | 163 | 212 | 294 |  |  |  |  | 2013-08-25 |  |  | Mule/horse searching
7 | Horsing | Horsing |  | Ispaya | Charazani | 4 | 5 | 6 |  |  |  | 25 | 101 |  | 111 | 2013-08-30
|  | Recovery | Charazani |  |  | 1 | 1 | 2 | [7 empty] | 2013-08-31
|  | Jungle Horsing |  | Charazani | Apolo | 11 | 12 | 14 |  |  |  | 15 | 181 |  | 199 | 2013-09-12
|  | Recovery | Apolo |  |  | 1 | 1 | 2 | [7 empty] | 2013-09-13 | May-Sep, ok Apr-Oct
|  | Walking |  | Apolo | Rurrenabaque | 8 | 9 | 12 |  |  |  | 25 | 163 |  | 195 | 2013-09-22
[5 empty] | Total | 25 | 28 | 36 | 188 | 240 | 330 |  |  |  | 505
| Transmission | Recovery | Rurrenabaque |  |  | 3 | 4 | 5 | 191 | 244 | 335 |  |  |  |  | 2013-09-26 | Jul-Sep, ok Apr-Oct |  | canoe searching
8 | Padling | Padling |  | Rurrenabaque | Riberalta | 20 | 23 | 26 |  |  |  | 35 | 825 |  | 830 | 2013-10-19
|  | Recovery | Riberalta |  |  | 1 | 2 | 3 | [7 empty] | 2013-10-21 | May-Sep, ok Apr-Oct |  | swaping canoe for bike
|  | Cycling |  | Riberalta | Porto Velho | 4 | 5 | 7 |  |  |  | 75 |  | 425 | 425 | 2013-10-26
|  | Recovery | Porto Velho |  |  | 1 | 2 | 3 | [7 empty] | 2013-10-28 | May-Oct |  | swaping bike for canoe
|  |  |  | Porto Velho | Manaus | 10 | 38 | 48 | [6 empty] | 1345 | 2013-12-05
| version 1 | Padling |  | Porto Velho | Bobra | 22 | 25 | 28 |  |  |  | 35 | 870 |  | 880
|  | Walking |  | Bobra | Manaus | 10 | 13 | 20 |  |  |  | 15 | 135 |  | 200 |  |  |  | Guide to be found
| version 2 | Padling |  | Porto Velho | Itacoatiara | 27 | 32 | 35 |  |  |  | 35 | 1085 |  | 1100
|  | skateboarding |  | Itacoatiara | Manaus | 7 | 8 | 11 |  |  |  | 30 |  | 245 | 245 |  |  |  | skate to be bought
| version 3 | Cycling |  | Porto Velho | Manaus | 10 | 12 | 17 |  |  |  | 60 |  | 860 | 860
[5 empty] | Total | 36 | 70 | 87 | 227 | 314 | 422 |  |  |  | 2600 | 485 km might be less
| Transmission | Recovery | Manaus |  |  | 2 | 4 | 5 | 229 | 318 | 427 |  |  |  |  | 2013-12-09 | Jun-Oct, ok May-Nov | CS to be found | skateboard, roll skate, bike search
9 | Cycling |  |  | Manaus | Santa Elena | 8 | 13 | 20 | [5 empty] | 1015 | 1015 | 2013-12-22
| version 1 | Cycling |  | Manaus | Santa Elena | 8 | 10 | 17 |  |  |  | 100 |  | 1015 | 1015 |  | Boa Vista Oct-Mar
| version 2 | Roller skating |  | Manaus | Presidente Figueiredo | 3 | 4 | 5 |  |  |  | 30 |  | 125 | 125
|  | Cycling |  | Presidente Figueiredo | Santa Elena | 7 | 9 | 15 |  |  |  | 100 |  | 890 | 890
[5 empty] | Total | 8 | 13 | 20 | 237 | 331 | 447 |  |  |  | 1015
| Transmission | Recovery | Santa Elena |  |  | 2 | 3 | 4 | 239 | 334 | 451 |  |  |  |  | 2013-12-25 | Jan-Mar, ok Sep-Dec | Edyta contact | Guide to be found
10 | Cycling |  |  | Santa Elena | Maicao | 16 | 50 | 66 | [6 empty] | 2120 | 2014-02-13
| version 1 | Cycling |  | Santa Elena | Maicao | 16 | 19 | 32 |  |  |  | 75 |  | 1930 | 1930
| version 2 | Paragliding |  | Santa Elena | around | 1 | 1 | 2 | [10 empty] | instructor to be found
|  | Walking/paddling |  | Santa Elena | Ciudad Bolivar | 25 | 34 | 40 |  |  |  | 25 | 794 |  | 860
|  | Recovery |  | Ciudad Bolivar |  | 1 | 2 | 3 | [8 empty] | Sep-Apr, ok May
|  | Cycling |  | Ciudad Bolivar | Maicao | 11 | 13 | 21 |  |  |  | 75 |  | 1260 | 1260 |  |  |  | bike to be arrange in C. Bolivar
[5 empty] | Total | 16 | 50 | 66 | 255 | 384 | 517 |  |  |  | 2120 | 190 km might be less
| Transmission | Recovery | Maicao |  |  | 1 | 1 | 3 | 256 | 385 | 520 |  |  |  |  | 2014-02-14 | Anytime |  | leave the bike somewhere
11 | Walking |  |  | Maicao | Punta Gallinas | 6 | 7 | 9 |  |  |  | 25 | 164 |  | 180 | 2014-02-21
[5 empty] | Total | 6 | 7 | 9 | 262 | 392 | 529 |  |  |  | 180
[5 empty] | Trip Grand Total |  |  |  | 262 | 392 | 529 |  |  |  | 13260 | 1015 km might be less
| Preparation | Start |  |  | depart Sydney | [10 empty] | 2012-12-31
|  | Flying |  | Sydney | Santiago | 0 | 0 | 2 | [7 empty] | 2012-12-31 |  |  | to be booked
|  | Preparation | Santiago |  |  | 2 | 4 | 5 | [7 empty] | 2013-01-04 |  |  | maps,boxes,food, bike, freight, car
|  | Driving South |  | Santiago | Punta Arenas | 7 | 18 | 18 | [7 empty] | 2013-01-22
|  | Preparation | Punta Arenas |  |  | 0 | 1 | 1 | [7 empty] | 2013-01-23 |  |  | CS to be found
|  | driving/hike |  | Punta Arenas | Cabo Froward | 2 | 2 | 4 | [7 empty] | 2013-01-25
[5 empty] | Total Preparation | 11 | 25 | 30
| Return home | Hitchhike/hike |  | Punta Gallinas | Maicao | 1 | 2 | 3 | [7 empty] | 2014-02-23
|  | Driving |  | Maicao | Bogota | 2 | 2 | 3 | [7 empty] | 2014-02-25
|  | Flying |  | Bogota | Santiago | 1 | 2 | 2 | [7 empty] | 2014-02-27
|  | Preparation |  | Santiago |  | 1 | 3 | 3 | [7 empty] | 2014-03-02
|  | Flying |  | Santiago | Sydney | 1 | 1 | 1 | [7 empty] | 2014-03-03
[5 empty] | Total return | 6 | 10 | 12
[5 empty] | Inc. Preparation and return |  |  |  | 279 | 427 | 571
Formulas:
Estimated date = SUM([Estimated date, row above]+H17)